## Project Schedule Template
Project Schedule for Team ABC
Week | Task Description | Responsibility | Est. Time
2017-10-10 | Submit second design report | whole team | -
| Submit purchase orders for any materials purchased outside of lab | someone's name | 10 min.
| Fabricate motor mount brackets | someone's name | 105 min.
| Fabricate wheel hubs (start) | someone's name | 105 min.
| Fabricate mobile platform (start) | someone's name | 105 min.
| Fabricate [Part Name] for ball manipulator | someone's name | 45 min.
| Fabricate [Part Name] for ball manipulator (start) | someone's name | 60 min.
| Meet outside lab to work through problems & review who's doing what next week, and prepare any necessary paperwork (POs, ECNs, etc.) | whole team | -
2017-10-17 | Fabricate wheel hubs (finish) | someone's name | 60 min.
| Fabricate mobile platform (finish) | someone's name | 15 min.
| Assemble motors, hubs & wheels and attach to mobile platform | someone's name | 45 min.
| Finish [Part Name] for ball manipulator | someone's name | 35 min.
| Fabricate [Part Name] for ball manipulator | someone's name | 30 min.
| Assemble Parts X, Y, Z for ball manipulator | someone's name | 40 min.
| Meet outside lab to work through problems & review who's doing what next week, and prepare any necessary paperwork (POs, ECNs, etc.) | whole team | -
ETCETERA ...
NOTES (DELETE AFTER READING & BEFORE PRINTING):
1. The times provided in this template are ficticious and only intended to show the type of detail necessary for a useful project schedule; update and use the manufacturing and assembly times your group estimated when completing the decision matrices.
2. Max work times (105 min) are based on 115 min. lab periods in Fall/Spring semester with 10 min. for clean-up at the end lab; adjust work times for 165 min. Summer terms.
3. Every manufactured part should appear in your team's project work schedule.
4. Account for holidays which fall on your formal lab periods, as well as the 45 min. welding demonstration noted in the course syllabus.
4. Account for holidays which fall on your formal lab periods, as well as the 45 min. welding demonstration noted in the course syllabus.
5. Every member should have scheduled work for the entire lab block until the team is ready to test.